## Sheet1
Planning Schedule
Start date
2018-11-25
Number of staff
100
2018-12-03 | 1st Meeting with Team (people, Space & Technology) determine business objectives.
Analysis of existing office environments.
Carry out a survey of existing office space.
Carry out a survey of usage of office space.
Analysis of Who What and Why & Where
Determine problems & excellence.
Locate common fixed assets.
Generate diagram of existing usage.
2018-12-11 | 2nd Meeting with Team.
Analysis of proposed office space.
Site Survey • Identify Individual specific needs of staff & identify unique working styles
2018-12-19 | 3rd Meeting with Team.
Propose style of working.
Provision of schematic drawings
Proposition of strategy for change.
4th Meeting With Team.
2019-01-11 | Provision of budgets and scope of works
Approvals and works
2019-01-21 | Formal approval of costs & proposed works
2019-01-29 | Commencement of build works
2019-03-04 | Relocation to new office space
© MICHAEL GREAVES & ASSOCIATES 2017

## Sheet2 (hidden)
| Staff Number | 100 | 100
| Start Date | 2018-11-25
| 2018-12-03 | 2018-11-25 | 1st Meeting with Team (people, Space & Technology) determine business objectives.
Analysis of existing office environments.
Carry out a survey of existing office space.
Carry out a survey of usage of office space.
Analysis of Who What and Why & Where
Determine problems & excellence.
Locate common fixed assets.
Generate diagram of existing usage.
| 2018-12-11 | 2018-12-02 | Analysis of proposed office space.
Site Survey • Identify Individual specific needs of staff & identify unique working styles
| 2018-12-19 | 2018-12-09 | Propose style of working.
Provision of schematic drawings
|  | 2018-12-16 | Proposition of strategy for change.
| 2019-01-11 | 2018-12-23 | Provision of budgets and scope of works
| 2019-01-21 |  | FORMAL ACCEPTANCE OF QUOTATION
| 2019-01-29 |  | POSESSION OF SITE FOR WORKS
| 2019-03-04 |  | HAND OVER OF FINISHED PROJECT
Holidays
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-26
2018-03-01
2018-03-30
2018-03-31
2018-04-01
2018-04-02
2018-05-25
2018-06-11
2018-09-28
2018-11-06
2018-12-20
2018-12-21
2018-12-22
2018-12-23
2018-12-24
2018-12-25
2018-12-26
2018-12-27
2018-12-28
2018-12-29
2018-12-30
2018-12-31
2019-01-01
2019-01-02
2019-01-03
2019-01-04
2019-01-05
2019-01-06
2019-01-07
2019-01-08
2019-01-09
2019-01-10
2019-01-26
2019-03-01
2019-03-30
2019-03-31
2019-04-01
2019-04-02
2019-05-25
2019-06-11
2019-09-28
2019-11-06
2019-12-20
2019-12-21
2019-12-22
2019-12-23
2019-12-24
2019-12-25
2019-12-26
2019-12-27
2019-12-28
2019-12-29
2019-12-30
2019-12-31
2020-01-01
2020-01-02
2020-01-03
2020-01-04
2020-01-05
2020-01-06
2020-01-07
2020-01-08
2020-01-09
2020-01-10
2020-01-26
2020-02-29
2020-03-29
2020-03-30
2020-03-31
2020-04-01
2020-05-24
2020-06-10
2020-09-27
2020-11-05
2020-12-19
2020-12-20
2020-12-21
2020-12-22
2020-12-23
2020-12-24
2020-12-25
2020-12-26
2020-12-27
2020-12-28
2020-12-29
2020-12-30
2020-12-31
2021-01-01
2021-01-02
2021-01-03
2021-01-04
2021-01-05
2021-01-06
2021-01-07
2021-01-08
2021-01-09